Project Charter

Employee Data Quality and Insights Project

Prepared by: Silas Olayoriju Bello

Date: 8/30/2025

### Project Purpose/ Objective

- To analyze and clean the employee data-set for completeness, accuracy and consistency.

- To generate insights that HR can use to make informed decisions on employee performance, salary trends and workforce distribution.

### Project Scope

- Cleaning inconsistent or missing employee data.

- Analyzing HR-related questions.

- Building a Dashboard for HR decision-making.

### Key Stakeholders

- Project Sponsor: HR Department

- Primary Users: HR Managers, Recruiters, Employee Relations Team

- Data Analyst/Project Manager: Silas Olayoriju Bello

### Deliverables

- Cleaned employee dataset

- HR insight report (with visualizations)

- Dashboard for quick workforce analytics

### Timeline (High-Level)

- Initiation and Planning: Sept 1 – Sept 3, 2025

- Data Preparation (Cleaning and Structuring): Sept 4 – Sept 10, 2025

- Analysis and Insights Development: Sept 11 – Sept 18, 2025

- Visualization and Dashboard Creation: Sept 19 – Sept 24, 2025

- Reporting and Closure: Sept 25 – Sept 30, 2025

### Risks

- Missing or incomplete employee data could limit insights.

- Inconsistent data format may slow down cleaning.

### Success Criteria

- Dataset is cleaned with no critical gaps.

- HR receives a clear, visualized report answering key workforce questions.

- Project completed within the agreed timeline.

### Tools/Resources

- Power BI (Power Query Editor & Data Modeling); for cleaning, transforming, analyzing data and creating HR dashboards.

- Excel (Project Tracker & Light Analysis); for simple project tracking (Gantt charts, task lists and timelines) and quick data checks before moving to Power BI.

- Trello; for agile task management and project tracking using boards/cards.

- GitHub; for documenting project progress and publishing portfolio-ready deliverables.

- Microsoft Word; for creating project documentation (Project Charter, Analysis Report and Final Write-up)

- Microsoft PowerPoint; for building a presentation deck, summarizing project goals, methods and insights.